## Sheet1
ID | Category | Sub-Category | Description | Location Identified | Opportunities/ Initiative | Owner(s) | Stakeholder(s) | Filtering-Stakeholder-Categories | Expected Timeline | Ease of Implementation (Low to High) | Impact (out of 10) | Metrics | Scope of Implementation | Preqrequisite initiative (s)
PR1 | Policy and Regulatory | Attitudes and Knowledge Gaps | There is a gap between the promotion of modular and the acceptance of it. Specifically, politicians have been promoting modular however their departments do not prefer it. A gap was also noted in CMHC promoting modular and accepting it. | Atlantic Region | Create an Approval Pathway supported by a regional modular knowledge + capacity system, including designer/manufacturer directories, technical guidance, and micro-credential training for planners, inspectors, and designers. Strengthen acceptance through a coordinated advocacy and public-awareness program, supported by a national council and government communications to debunk outdated perceptions. | Provincial Housing Departments Municipal Affairs | Municipal planning departments building officials, manufacturers, CMHC regional staff | Municipal Government, Provincial Government, Federal Government, Manufacturers | 2027 | Medium | 9 | Number of projects approved Approval time Number of departments using pathway | Regional | Development of clear eligibility criteria for selecting modular demonstration projects. Creation of a standardized modular submission package for applicants. Preparation of a modular review checklist for inspectors and permitting staff.
PR2 | Policy and Regulatory | Attitudes and Knowledge Gaps | Lack of alignment in terminology from funders. Ambiguity in terminology leading to confusion. | NB | Standardize all modular/off-site terminology and require all provincial funding programs, municipal planning departments, and development officers to use the same definitions. Create an Atlantic Code Interpretation Bank where building officials share consistent rulings. | NB Department of Local Government and Local Governance Reform (DLGLR) | Municipal planning departments, development officers, NB Housing, CMHC regional office, NB Building Officials Association, developers & modular manufacturers | Municipal Government, Provincial Government, Federal Government, Manufacturers, Developers & General Contractors | 2026 | High | 7 | Number of municipalities adopting the terminology Reduction in terminology-related rejections Consistency in NB Housing program applications | Local, provincial | Drafting of a concise modular terminology list based on CSA standards. Internal review by NB Housing, DLGLR, and municipal planners to confirm usability. Development of a short implementation memo instructing municipalities to adopt the terminology.
PR3 | Policy and Regulatory | Attitudes and Knowledge Gaps | Lack of emphasis of the impact of housing on population health | NB | Develop an NB Healthy Housing Planning Note that outlines how housing supply, overcrowding, and delays influence population health outcomes. | NB Office of the Chief Medical Officer of Health (Public Health) NB Department of Local Government & Local Governance Reform (DLGLR) | Regional Planning Commission, development officers, NB Housing, municipal councils, public health officers | Municipal Government, Provincial Government | 2026 | High | 6 | Number of planning decisions referencing the Note. | Provincial | Drafting of the Healthy Housing Planning Note by NB Public Health with input from planning staff. Review and approval by DLGLR for integration into municipal planning processes. Distribution and short briefing session for development officers and planning commissions.
PR4 | Policy and Regulatory | Codes and Standards | Complexity of codes: mention of challenges navigating national, provincial, and local codes (including NBC, NECB). | Atlantic Region | Develop an Atlantic Modular Code Navigation Guide (AMCNG) that clarifies how modular/off-site construction complies with NBC, NECB and municipal requirements. | Department of Public Safety (NB) Department of Municipal Affairs and Housing (NS) Department of Housing, Land and Communities (PEI) Service NL (NL) | Building officials, municipal plan reviewers, housing departments, modular manufacturers, consulting engineers | Provincial Government, Technical Professionals, Manufacturers | 2027 | Medium | 8 | Change in average permit review times for modular projects (before vs after guide) Number of municipalities that formally adopt or reference the AM-CNG in procedures Number of RFIs or code-related clarifications requested on modular submissions (aim: decrease) Number of building officials / plan reviewers trained using the guide | Regional | Inventory of existing modular-related code interpretations and issues Inventory of existing modular-related code interpretations and issues Draft modular-specific code navigation guide for review Pilot the guide with a small set of municipalities / projects
PR5 | Policy and Regulatory | Codes and Standards | Challenges related to codes and standards differing between provinces and municipalities. In addition to accessibility codes and seismic requirements differing across the country. | NS | Develop an Atlantic Modular Design Acceptance Note in Navigation Guide that provides clear guidance for how modular units designed in other provinces especially those with different seismic, accessibility, or energy requirements should be reviewed and accepted across Atlantic jurisdictions. This supplements the Atlantic Modular Code Navigation Guide (PR4) by addressing cross-border design differences, ensuring consistent treatment of modular systems entering NS, NB, PEI, and NL. | Department of Public Safety (NB) Department of Municipal Affairs and Housing (NS) Department of Housing, Land and Communities (PEI) Service NL (NL) | Building officials, municipal plan reviewers, housing departments, modular manufacturers, consulting engineers, architects | Provincial Government, Technical Professionals, Manufacturers | 2027 | Medium | 8 | Number of municipalities that formally adopt it Reduction in modular projects flagged for seismic/accessibility differences Reduction in RFIs for out-of-province modular submissions Approval timelines (before vs after) | Regional | Identify common conflicts when modular units enter the Atlantic region (seismic, accessibility, energy). Regional meeting with code officials to agree on acceptable approaches. Draft the Modular Design Acceptance Note. Pilot with 1 or 2 cross-border modular projects (e.g., manufactured in NB → installed in NS).
PR6 | Policy and Regulatory | Government Coordination | Lack of communication across government agencies. | Atlantic Region | Establish an quarterly virtual meeting where housing, planning, code, and procurement representatives from each province review modular-related issues, clarify who leads on cross-department questions, and align upcoming policy/approval changes that affect modular construction. Add Provincial Modular Point-of-Contact Offices to streamline interdepartmental communication and reduce approval delays. | Department of Public Safety (NB) NB Housing Department of Municipal Affairs and Housing (NS) Department of Housing, Land and Communities (PEI) Service NL (NL) Newfoundland and Labrador Housing Corporation (NLHC) | Provincial Building Code / Technical Standards branches, Municipal Affairs / Municipal Planning divisions, provincial procurement units, municipal planning commissions Atlantic Building Officials Association, modular manufacturers, key federal partners (CMHC Atlantic) | Provincial Government, Municipal Government, Manufacturers, Federal Government | 2026 | High | 8 | Number of coordination meetings held Number of cross-department issues resolved Feedback from departments on clarity of roles | Regional | Identify representatives from Housing, Planning, Code, and Procurement in each province. Agree on basic Terms of Reference (purpose: modular-related coordination only). Create a shared information template for departments to submit updates/issues. Schedule quarterly virtual meetings (Atlantic-wide).
PR7 | Policy and Regulatory | Government Coordination | Outdated policies needing to be updated. | NL | Designate a Modular Liaison Officer within Service NL’s Built Environment Division to act as the single point of contact for resolving issues caused by outdated provincial or municipal policies. The role provides clear interpretations, coordinates with NL Housing and municipalities, guides modular projects through outdated processes, and identifies which policies require modernization. | Service NL - Built Environment Division NL Housing Corporation | Municipal building officials, municipal planning departments, provincial procurement division, NL Housing project managers, modular manufacturers delivering to NL, Office of the Fire Commissioner | Provincial Government, Technical Professionals, Municipal Government | 2026 | High | 7 | Number of modular projects supported by the liaison Reduction in RFI volume related to outdated policies Faster issue resolution times (before vs after designation) Reduction in approval delays | Provincial | Assign an existing staff member in Service NL as Modular Liaison Officer (no new hiring needed). Establish mandate: resolve outdated-policy conflicts, coordinate with NL Housing, guide modular projects. Set up an intake channel like email or form for modular-related questions. Hold initial coordination meetings with NL Housing and priority municipalities. Start tracking outdated policies to inform future modernization efforts.
PR8 | Policy and Regulatory | Inspections | Operational complexity with prefab due to multiple contractors and on-site and off-site teams. | NS | Develop a Modular Construction Coordination Protocol that clearly outlines how off-site teams (factory, transport, installation) and on-site teams (site contractor, municipal staff) communicate, hand off responsibilities, and sequence their work on modular projects. The protocol would define who is responsible at each stage of the process, when information must be shared, how factory documentation (e.g., CSA A277) is integrated into municipal reviews, and how installation activities are coordinated to reduce overlap, uncertainty, and delays. | NS Department of Municipal Affairs & Housing – Building and Technical Standards Division Office of the Fire Marshal Nova Scotia Provincial Housing Agency | NS Building Officials Association, municipal building officials & development officers, modular manufacturers shipping into NS, general contractors & installation crews, electrical and plumbing inspectors (as needed), NSPHA project managers | Provincial Government, Technical Professionals | 2026 | Medium | 8 | Reduction in coordination issues reported. Reduction in duplicated site activities or installation delays Faster turnaround for modular installation scheduling Number of municipalities using it. Feedback from contractors and building officials on clarity | Provincial | Map existing modular workflows (factory → transport → installation → municipal inspection → site finishing). Identify common coordination problems across NS municipalities. Draft a unified workflow, responsibility matrix, and communication sequence. Engage NS Building Officials Association and municipalities for review. Pilot the protocol on 1–2 NSPHA modular projects and refine. Roll out province-wide through municipal channels and inspector associations.
PR9 | Policy and Regulatory | Inspections | Concerns about duplicate inspections resulting in inefficiencies | Atlantic Region | Create an Atlantic Modular Inspection Acceptance Framework that clarifies which inspections completed under CSA A277 (factory QA) must be accepted by municipalities across Atlantic Canada, and which inspections must be performed on-site only. | Nova Scotia Building Officials Association New Brunswick Building Officials Association Municipal Building Officials Association of Prince Edward Island Newfoundland and Labrador Building Officials Association Department of Public Safety (NB) Department of Municipal Affairs and Housing (NS) Department of Housing, Land and Communities (PEI) Service NL (NL) | Municipal building officials across Atlantic Canada, modular manufacturers (CSA A277 certified), installation contractors, NSPHA, NB Housing, PEI Housing, NL Housing, Office of the Fire Marshal (provincial), developers using modular systems | Provincial Government, Manufacturers, Developers & General Contractors | 2027 | Medium | 9 | Reduction in duplicated inspection steps % of Atlantic municipalities using the acceptance framework Shortened inspection timelines for modular projects Fewer RFI (Requests for Information) from inspectors Improved manufacturer feedback on municipal acceptance | Regional | Map which inspections are already covered under CSA A277 (factory QA, structural, plumbing rough-ins, electrical pre-wiring, firestopping inside modules). List which inspections MUST remain on-site (foundation, hookups, sealing, fire separations, assembly). Review differences in inspection practices across Atlantic municipalities. Draft the shared Framework
PR10 | Policy and Regulatory | Inspections | Cost barriers and lack of incentives to becoming CSA certified. | NL | Provide a small CSA A277 Certification Rebate for manufacturers that successfully complete certification. This lowers the up-front financial barrier and incentivizes more NL-based plants to become certified. | Service NL | Local manufacturers, NL Housing Corporation, CSA Group, modular installers | Provincial Government, Manufacturers | 2027 | Medium | 8 | Number of manufacturers receiving rebate Number of manufacturers getting CSA certification Increase in modular supply in NL | Provincial | Define the rebate criteria, including which manufacturers are eligible and what conditions must be met. Confirm which certification costs are eligible. Set up a simple application form so manufacturers can submit proof of certification to receive the rebate.
PR11 | Policy and Regulatory | Inspections | Concerns that inspections done on components in factory instead of the whole building could lead to hidden issues which may emerge when components are combined. | NS | Create a simple inspection checklist for Nova Scotia that outlines the specific on-site checks required after modules are set (e.g., fire separations, sealing, structural connections, plumbing/electrical tie-ins). This reassures inspectors that all critical elements are verified on-site and reduces concerns about hidden issues that weren’t visible during factory inspections. | NS Department of Municipal Affairs & Housing - Building & Technical Standards Division NS Building Officials Association (NSBOA) | Municipal building officials, modular manufacturers supplying NS, general contractors & installation crews, Office of the Fire Marshal | Provincial Government, Municipal Government, Developers & General Contractors | 2026 | High | 9 | Number of inspectors using the checklist Reduction in duplicated full building reinspections | Local, provincial | Identify which assembly-stage checks commonly cause concern for inspectors. Draft a short checklist with NSBOA input. Test it on 1–2 modular installations.
PR12 | Policy and Regulatory | Permitting and Approvals | Slow and costly approval processes | Atlantic Region | Create a modular permitting track where repeatable modular designs that have pre-verified structural, fire, and energy compliance (e.g., CSA-certified modules) receive shorter review timelines. | Municipal Building & Permitting Departments Provincial Housing Agencies Provincial Departments of Municipal Affairs | Manufacturers, developers, architects, engineers,permitting officials, general contractors. | Provincial Government, Municipal Government, Technical Professionals, Developers & General Contractors | 2027 | Medium | 9 | Average modular permitting time before vs. after track Number of repeatable modular designs pre-verified Increase in modular applications submitted | Local, provincial | Identify which modular designs can be pre-verified. Provide municipalities with CSA certification details. Update municipal workflows to skip factory-completed checks.
PR13 | Policy and Regulatory | Permitting and Approvals | Municipal zoning rules restrict certain housing types, proximity requirements, or have unclear procedures between zoning and permitting steps. | Atlantic Region | Create a clear Modular Zoning Interpretation Guide for Atlantic region municipalities that explains how modular housing fits into existing zoning categories, what housing types are permitted, and the exact steps from zoning review to building permit. Integrate pre-approved modular design templates and guidance on modular suitability by housing type and site condition. | Municipal planning departments Provincial planning/technical standards divisions | Developers, modular manufacturers, development officers, municipal planners, building officials | Provincial Government, Municipal Government, Technical Professionals, Developers & General Contractors | 2026 | High | 9 | Improved clarity in pre-application reviews | Local, provincial, regional | Review existing zoning categories across sample municipalities. Identify where modular fits (e.g., single-unit, multi-unit, accessory). Validate with municipal planners and development officers.
PR14 | Policy and Regulatory | Permitting and Approvals | Unclear processes: multiple layers of government or departments involved, unclear distinctions/responsibilities between codes, bylaws, and approval pathways. | Atlantic Region | Expand the Atlantic Modular Code Navigation Guide (developed in PR4) to include a Modular Approval Pathway section outlining which departments are involved, what each is responsible for, and the step-by-step process from zoning review to building permit and occupancy. | Department of Public Safety (NB) Department of Municipal Affairs and Housing (NS) Department of Housing, Land and Communities (PEI) Service NL (NL) | Municipal planners and development officers, building officials, modular manufacturers, developers, provincial housing agencies | Provincial Government, Municipal Government, Manufacturers, Developers & General Contractors | 2026 | High | 9 | Reduction in process-related RFIs for modular files | Local, provincial, regional | Review current approval steps across select municipalities. Define departmental roles and responsibilities clearly. Draft the Approval Pathway section and integrate it into the PR4 Navigation Guide. Validate with municipal planners and building officials.
PR15 | Policy and Regulatory | Permitting and Approvals | Heritage Conservation Act identifies heritage places in unincorporated areas, providing a barrier for housing. | NB | Add a Heritage Requirements Check section to the NB version of the Navigation Guide that clearly explains when heritage rules apply in unincorporated areas, what permits may be needed (site alteration, archaeology), expected timelines, and when developers must notify the province. | NB Department of Tourism, Heritage and Culture - Heritage Branch NB Department of Public Safety - Building Code Administration | Developers, municipalities planning staff, odular manufacturers, NB Housing, archaeology and heritage consultants | Provincial Government, Developers & General Contractors, Technical Professionals | 2026 | High | 7 | Reduction in unplanned heritage-related delays Fewer RFIs to the Heritage Branch | Provincial | Confirm which heritage triggers apply in unincorporated areas Summarize permit types (site alteration, impact assessment) Draft short guidance text for Navigation Guide Validate with NB Heritage Branch
FI1 | Financing and Insurance | Access to Financing | Banks and lenders do not fully understand or accept modular/off-site construction because of high perceived risks in OSC. | Atlantic Region | Develop an Atlantic Modular Lending Brief that explains modular construction timelines, factory QA (CSA A277), and risk profiles in plain language so lenders understand modular projects better and gain confidence in financing them. Enable alternative financing models like vendor financing options and structured payment guidance for lenders. | Provincial Departments of Finance Atlantic Credit Union Associations | Major banks (RBC, TD, Scotiabank, CIBC, BMO), regional credit unions, developers & modular manufacturers, CMHC (reference alignment) | Provincial Government, Finance & Insurance/Business Services, Federal Government | 2026 | High | 8 | Number of lenders adopting the brief Reduction in financing rejections for modular Increase in modular mortgage approvals | Regional | Gather modular timeline + risk data from manufacturers
FI2 | Financing and Insurance | Access to Financing | Limited financing options for small-scale ownership (e.g., single units, duplexes) force many buyers to rely on high-interest lenders. | Atlantic Region | Use the Atlantic Modular Lending Brief to help lenders understand how single-unit and small-scale modular builds work, encouraging them to create better mortgage options for small modular homes instead of directing buyers to high-interest lenders. | Provincial Departments of Finance Atlantic Credit Union Associations | First-time buyers, credit unions (large role), mortgage brokers, modular manufacturers, community development agencies | Provincial Government, Finance & Insurance/Business Services, Manufacturers | 2026 | High | 8 | Increase in number approved modular mortgages under 2 units | Regional
FI3 | Financing and Insurance | Access to Financing | Financing rules, mortgage products, and banking policies are outdated for OSC. | Atlantic Region | Use the Atlantic Modular Lending Brief to modernize lender policies by clearly explaining modular payment schedules, delivery timelines, and draw structures so banks can update outdated mortgage products to fit off-site construction. | Provincial Departments of Finance | Major banks (RBC, TD, Scotiabank, CIBC, BMO), regional credit unions, developers & modular manufacturers, CMHC (reference alignment) | Provincial Government, Finance & Insurance/Business Services, Federal Government | 2026 | High | 9 | Reduction in modular project financing delays | Regional | Build a sample modular draw schedule Document cash-flow needs for modular builds
FI4 | Financing and Insurance | Access to Financing | Lack of competition among funding providers. | NS | Share the Atlantic Modular Lending Brief with credit unions and regional lenders to help them enter the modular lending space, increasing competition and giving developers more financing choices in Nova Scotia. | Nova Scotia Department of Finance | NS credit unions, local lenders & community investment funds, developers, modular manufacturers | Provincial Government, Finance & Insurance/Business Services, Manufacturers | 2026 | High | 7 | Reduced reliance on one or two banks Increase in competitive interest rates for modular | Provincial | Prepare NS-specific version of the brief
FI5 | Financing and Insurance | Cost Structure | High upfront costs and misaligned payment milestones strain cash flow. | Atlantic Region | Add Modular Payment Framework section to the Atlantic Modular Lending Brief that recommends modular-friendly draw schedules (e.g., factory start, 50% fabrication, delivery, installation) that aligns with draw schedules with factory milestones and modular timelines. Add liquidity supports such as working-capital credit lines and allow using incentives as upfront deposits to reduce cashflow strain. | Provincial Departments of Finance Credit Union Associations | Manufacturers, developers, lenders, CMHC, Construction managers | Provincial Government, Finance & Insurance/Business Services, Federal Government, Developers & General Contractors | 2026 | High | 9 | Number of lenders adopting modular-friendly draw schedules Reduced delays caused by payment timing | Regional | Document typical modular cost curves Build standard modular draw templates
FI6 | Financing and Insurance | Cost Structure | Challenges producing accurate pricing estimates due to immature market. | Atlantic Region | Develop an Modular Cost Libraries that provides standardized cost ranges and inputs for modular projects across the region (e.g., module $/sqft bands, transport and crane costs, installation costs, contingencies, island delivery uplifts, and seasonal adjustments). | Provincial Departments of Finance | Modular manufacturers (input providers), Developers / builders, quantity surveyors, housing agencies (NB Housing, NSPHA, PEIHC, NLHC), lenders (for underwriting consistency) | Manufacturers, Developers & General Contractors, Provincial Government, Finance & Insurance/Business Services | 2026 -2028 | Medium | 8 | Number of manufacturers using the directory Reduction in estimate variability between suppliers Fewer lender RFIs about project costing | Regional | Collect baseline cost data from Atlantic manufacturers (module production, transport, installation). Create standardized cost bands (Low/Medium/High) for modules, logistics, and site work.
FI7 | Financing and Insurance | Cost Structure | Multi-unit modular construction significantly more expensive. | PEI | Create a delivery program that coordinates ferry bookings, transport, and crane scheduling across multiple modular projects. By pooling shipments and sharing installation logistics, PEI can reduce the island cost premiums | PEI Housing Corporation PEI Department of Transportation & Infrastructure PEI Procurement | PEI modular developers, general contractors, non-profits and community housing providers, transport companies & crane operators, ferry operators (Marine Atlantic if applicable for interprovincial shipments), modular manufacturers supplying to PEI | Manufacturers, Developers & General Contractors, Provincial Government, Finance & Insurance/Business Services, Transportation & Logistics Providers | 2027 | Medium | 9 | Reduction in module transport cost Number of projects participating in shared logistics Increased adoption of modular for multi-unit builds | Provincial | Map annual modular demand (public + private) in PEI Identify suppliers shipping to PEI and shipment patterns Pre-negotiate ferry/logistics windows Pre-qualify crane + install contractors willing to participate Develop cost-sharing model among participating projects
FI8 | Financing and Insurance | Cost Structure | Bonding challenges for small manufacturers | NS,NB | Create a Modular Supplier Pre-Qualification Pathway that allows small manufacturers to bid on provincial housing projects using factory QA certification, audited capacity, and past performance instead of full bonding. | Provincial Housing Agencies (NSPHA, NB Housing) Provincial Procurement Divisions | Small modular manufacturers, developers, general contractors, insurers, lenders | Manufacturers, Provincial Government, Finance & Insurance/Business Services | 2026 | Medium | 8 | Number of modular tenders allowing pre-qualified suppliers without full bonding Increase in bid participation Reduced project cancellations due to lack of bonded bidders | Provincial | Define modular-specific qualification criteria Review manufacturer QA, capacity, and safety documentation
FI9 | Financing and Insurance | CMHC Misalignment | CMHC policies do not align with OSC timelines, delivery methods, or cost structure. | Atlantic Region | Establish a Modular Program Coordination Group between CMHC and Atlantic provincial housing agencies to align CMHC program timelines with modular delivery. The group would review modular production schedules, identify approval bottlenecks, and develop modular-friendly review timelines and draw schedules so CMHC programs better reflect off-site construction workflows. | CMHC Regional Office Atlantic Provincial Housing Agencies | Modular manufacturers, developers, lenders, municipal planners, project managers | Federal Government, Developers & General Contractors, Finance & Insurance/Business Services, Technical Professionals | 2026 | Medium | 9 | Reduced CMHC approval time for modular files Increase in successful modular applications | Regional | Collect standard modular factory timelines from local manufacturers Compare with CMHC approval timelines Identify specific misalignment points Draft modular timeline recommendations
FI10 | Financing and Insurance | CMHC Misalignment | Restrictions on funding non-residential space in new buildings. | Atlantic Region | Use the Modular Program Coordination Group to develop clear, consistent criteria for evaluating mixed-use modular buildings (e.g., commercial ground floors + modular residential above), ensuring CMHC and provincial partners apply uniform rules in small Atlantic communities where mixed-use zoning is common. | CMHC Atlantic Provincial Housing Agencies Municipal planning | Developers, modular manufacturers, project teams | Developers & General Contractors, Manufacturers, Provincial Government, Federal Government, Municipal Government | 2026 | High | 7 | Fewer CMHC refusals due to non-residential shares | Regional | Gather PEI/NS/NB/NL examples of mixed-use zoning conditions Identify CMHC concerns about non-residential % Provide modular project examples to CMHC for comparison
FI11 | Financing and Insurance | CMHC Misalignment | Lack of clarity on how to access CMHC programs and funding streams. | Atlantic Region | create a simplified CMHC Access Guide for Atlantic developers that outlines which CMHC programs accept modular, required documents, typical underwriting questions, and common errors that providing a clear, region-specific navigation route | CMHC Regional Office Atlantic Provincial Housing Agencies | Developers, modular manufacturers, municipalities, lenders | Provincial Government, Federal Government, Developers & General Contractors, Finance & Insurance/Business Services | 2026 | High | 8 | Reduction in incomplete CMHC submissions Higher approval rates for modular files | Regional | Consolidate CMHC documentation requirements Summarize modular-specific questions asked by CMHC
FI12 | Financing and Insurance | CMHC Misalignment | CMHC data for rural areas is outdated/incorrect. | Atlantic Region | Use the Modular Program Coordination Group to share updated rural rent, vacancy, and population data from provincial housing agencies with CMHC’s underwriting team. | Provincial Housing Departments CMHC | Municipalities, regional planning commissions, developers | Federal Government, Developers & General Contractors, Technical Professionals | 2026 | Medium | 9 | More rural modular projects approved | Regional | Gather updated rural housing data Compare with CMHC’s national dataset Provide corrected figures
FI13 | Financing and Insurance | Insurance | There are coverage gaps, overlapping insurance requirements, and unclear responsibility transfers between the factory, transporter, and on-site contractor. | Atlantic Region | Create a unified modular insurance model that uses one project-wide policy and clear liability transfer points between factory, transport, and on-site construction | Insurance brokers specializing in construction Warranty providers Developers Modular manufacturers | Manufacturers, transporters, crane companies, general contractors, warranty providers, lenders, CMHC | Manufacturers, Transportation & Logistics Providers, Finance & Insurance/Business Services, Federal Government, Developers & General Contractors | 2026 | Medium | 9 | Number of modular projects using wrap-up all-risk coverage Reduction in duplicated premiums Fewer liability disputes Warranty acceptance rate for modular modules Lower overall insurance cost per unit | Regional | Manufacturers + developers jointly approach insurance brokers Brokers prepare integrated wrap-up policy options Legal teams insert handover protocol clauses into modular contracts
FI14 | Financing and Insurance | Insurance | Higher insurance premiums for mass timber or wood-based modular systems. | Atlantic Region | Work with insurers to introduce a modular mass-timber “risk-reduction credit” for factories and projects that meet specific fire-safety and loss-prevention controls (e.g., sprinklered fabrication areas, heat detection, dust suppression, certified flame-spread materials) which can lower premiums for wood-based modular systems. | Insurance brokers Major insurers operating in Atlantic Canada Modular manufacturers | Manufacturers, developers, lenders, warranty providers, provincial housing agencies. | Manufacturers, Developers & General Contractors, Finance & Insurance/Business Services, Provincial Government | 2026 | Medium | 8 | Reduction in builder’s-risk premiums for mass-timber modular Number of factories certified with risk-reduction controls Number of projects qualifying for the credit | Regional | Factory fire-safety and dust-control audit by insurer or broker Submission of technical documentation (sprinkler specs, dust-suppression protocols, flame-spread certificates) Insurer approval of risk-reduction credit structure
FI15 | Financing and Insurance | Insurance | Insurance regulations not tailored to offsite fabrication risks. | Atlantic Region | Work with the Insurance Bureau of Canada (IBC) and commercial insurers to create a specific classification for modular/off-site manufacturing facilities, reflecting their controlled, lower-risk environment. | Insurance Bureau of Canada Commercial insurers Insurance brokers | Manufacturers, developers, lenders, warranty providers, provincial housing agencies. | Manufacturers, Developers & General Contractors, Provincial Government, Finance & Insurance/Business Services | 2026 | Medium | 9 | Reduction in premiums for modular factories Number of factories moved to the new risk category | Regional | Factory safety audit and documentation (sprinklers, dust control, QC systems) Submission of technical facility data to IBC Development of a recommended classification description with brokers
FI16 | Financing and Insurance | Incentives & Policy | No tax incentives, subsidies, or financial supports tailored to modular/off-site. | Atlantic Region | Introduce a modular production credit (per module or per unit) for early-stage modular projects delivered to provincial housing agencies. | Nova Scotia Provincial Housing Agency New Brunswick Housing Corporation PEI Housing Corporation NL Housing Corporation Provincial Departments of Finance | Modular manufacturers, developers, non-profits, lenders, municipal housing partners, CMHC | Manufacturers, Provincial Government, Federal Government, Indigenous & Community Organizations, Developers & General Contractors | 2027 | Medium | 8 | Number of modular units delivered under the credit Reduction in per-unit cost for provincial housing builds Increase in manufacturer production volume | Provincial, regional | Determine per-unit credit value (e.g., $2,000–$5,000/unit) Set eligibility (affordable housing, supportive housing, repeatable modular designs) Secure small annual budget allocation Develop simple claim process at delivery or installation
FI17 | Financing and Insurance | Incentives & Policy | Government fees add affordability challenges. | Atlantic Region | Create a modular track fee adjustment so modular projects that meet repeatable designs and pre-verified code compliance (e.g., certified plans, CSA A277 compliance, approved modular typologies) qualify for reduced or capped permit and development fees. | Municipal Planning & Permitting Departments Provincial Housing Agencies (NSPHA NB Housing PEI Housing NL Housing) Provincial Departments of Municipal Affairs | Developers, manufacturers, municipal building officials, lenders. | Municipal Government, Developers & General Contractors, Finance & Insurance/Business Services | 2026 | Medium | 7 | Number of modular projects qualifying for adjusted fees Reduction in average fees paid per modular project Decrease in municipal review time per project Increase in modular applications submitted | Provincial, regional | Define what qualifies as “repeatable modular design” Establish pre-verified plan sets or modular typologies Update municipal fee schedules to include modular track
PM1 | Procurement Models and Contracts | Competition and Market Dynamics | Only few CSA-certified modular manufacturers, limiting competition, raising costs, and preventing suppliers from scaling confidently. | Atlantic Region | Pre-approve additional CSA A277 certified modular manufacturers from outside Atlantic Canada (e.g., Ontario, Quebec) to increase the supplier pool for provincial housing projects. Establish modular vendor pools/framework agreements for multi-year procurement and stable supplier participation. | NSPHA NB Housing PEI Housing NL Housing Provincial Procurement Divisions | Local modular manufacturers, out-of-region CSA-certified firms, developers, general contractors, lenders. | Manufacturers, Developers & General Contractors, Finance & Insurance/Business Services | 2026 | High | 9 | Increase in number of pre-qualified modular suppliers Reduction in average bid prices Number of projects receiving more than 1–2 bids | Regional | Compile list of CSA A277/A660-certified manufacturers in ON/QC Create modular-specific pre-qualification criteria Issue pre-qualification call
PM2 | Procurement Models and Contracts | Competition and Market Dynamics | Low-bid procurement models make modular solutions less competitive than traditional builds as modular construction has high upfront costs. | Atlantic Region | Require bidders to show factory costs, site costs, transport, and installation as separate line items in their price submission. This allows evaluators to understand why modular has higher early costs and prevents modular bids from being rejected. | NSPHA NB Housing PEI Housing NL Housing Provincial Procurement Divisions | Developers, modular manufacturers, general contractors, cost consultants, municipal housing partners | Developers & General Contractors, Manufacturers, Provincial Government, Federal Government, Municipal Government | 2026 | High | 9 | Number of RFPs using separated cost line items Increase in modular bids submitted Reduction in modular bid disqualification due to upfront costs | Regional | Update procurement templates to require separated cost line items Provide short internal guidance to evaluators
PM3 | Procurement Models and Contracts | Competition and Market Dynamics | Unclear demand and supply conditions create a “chicken-or-egg” problem, limiting competition and complicating procurement planning. | Atlantic Region | Publish a rolling 2–3 year forecast of upcoming modular-suitable public housing projects (non-binding) so manufacturers can see upcoming demand, plan capacity, and invest confidently. | Provincial Housing Agencies (NSPHA, NB Housing, PEI Housing, NLHC) Provincial Procurement Divisions Departments of Municipal Affairs & Housing | Modular manufacturers, developers, lenders, general contractors, municipalities. | Provincial Government, Manufacturers, Developers & General Contractors, Municipal Government | 2026 | High | 9 | Number of modular projects included in forecast Manufacturer participation in bids Increase in factory expansion/production planning | Regional | Identify which upcoming public housing projects are modular-compatible Collect capital plans from municipalities + provinces
PM4 | Procurement Models and Contracts | Competition and Market Dynamics | Projects may need to be approved as design-build to create more competition. | NS | Use design–build procurement for modular-suitable projects so manufacturers and modular-experienced contractors can participate early in the design. | Nova Scotia Provincial Housing Agency Nova Scotia Procurement (Service Nova Scotia) | Modular manufacturers, planners, developers, municipalities, provincial land agencies | Provincial Government, Manufacturers, Developers & General Contractors, Municipal Government | 2026 | High | 7 | Increase in number of modular bidders Reduction in redesign hours or change orders | Provincial | Identify modular-suitable projects early Issue RFPs using design–build method
PM5 | Procurement Models and Contracts | Competition and Market Dynamics | Limited land availability reduces how many modular projects can be procured. | NS | Identify small provincial and municipal sites that are already serviced or partially serviced, confirm their basic suitability for modular construction, and issue modular tenders. | Nova Scotia Provincial Housing Agency Municipalities Department of Public Works / Municipal Affairs | Modular manufacturers, design–build contractors, architects, engineers, developers, municipalities. | Provincial Government, Manufacturers, Technical Professionals, Municipal Government | 2026 | Medium | 7 | Number of parcels identified and pre-cleared Number of parcels included in modular tenders Increase in modular-suitable land availability | Provincial | Inventory small provincial & municipal parcels Basic servicing and access assessments Municipal confirmation of allowable uses
PM6 | Procurement Models and Contracts | Competition and Market Dynamics | Lack of accurate pricing from subtrades. | PEI | Develop an Modular Cost Libraries that provides standardized cost ranges and inputs for modular projects across the region (e.g., module $/sqft bands, transport and crane costs, installation costs, contingencies, island delivery uplifts, and seasonal adjustments). | Provincial Departments of Finance | Modular manufacturers, developers / builders, quantity surveyors, housing agencies (NB Housing, NSPHA, PEIHC, NLHC), lenders | Manufacturers, Developers & General Contractors, Provincial Government | 2026 -2028 | Medium | 8 | Number of manufacturers using the directory Reduction in estimate variability between suppliers Fewer lender RFIs about project costing | Regional | Collect baseline cost data from Atlantic manufacturers (module production, transport, installation). Create standardized cost bands (Low/Medium/High) for modules, logistics, and site work.
PM7 | Procurement Models and Contracts | Design and Standards | Designs are developed for traditional construction and only adapted to modular later which causes major redesign and infficiences. | Atlantic Region | Require modular-suitable projects to complete modular feasibility during early design stage. | Provincial Housing Agencies Municipal Housing Units Architectural teams Provincial Procurement Divisions | Architects, engineers, modular manufacturers, developers, general contractors. | Technical Professionals, Manufacturers, Developers & General Contractors, Provincial Government | 2026 | Medium | 9 | Fewer redesign hours Reduction in change orders Number of projects identifying modular feasibility early | Regional | Early design teams receive modular design parameters (grid, module sizes, MEP zones) Consultation with manufacturers during concept design Include modular feasibility as a required step in RFP scopes
PM8 | Procurement Models and Contracts | Design and Standards | Lack of modular-friendly designs and prescriptive requirements causes redesign, inefficiencies, and excludes modular methods. | Atlantic Region | Allow performance-based criteria so architects can design modular-friendly layouts from the start instead of trying to fit modular into traditional specifications. | Provincial Housing Agencies Municipal Housing Units Architectural teams Provincial Procurement Divisions | Architects, engineers, modular manufacturers, developers, general contractors. | Technical Professionals, Manufacturers, Developers & General Contractors, Provincial Government | 2026 | Medium | 9 | Number of RFPs using performance-based criteria Reduction in redesign hours Fewer modular bids rejected due to prescriptive design conflicts Increase in modular participation in tenders | Regional | Update design scopes to remove prescriptive structural and layout requirements Provide architects a set of modular design parameters (module sizes, grid, spans) Include modular considerations during concept/schematic design stages
PM9 | Procurement Models and Contracts | Design and Standards | Modular builds from other regions may not be designed to meet local performance standards (e.g., hurricane-force winds ). | NS, NL | Require out-of-province modular bidders to submit structural and envelope verification stamped to Atlantic wind, snow, and coastal exposure requirements as part of their proposal. | Provincial Housing Agencies Municipal Building/Permitting Departments Provincial Procurement Divisions | Structural engineers, modular manufacturers, permitting officials, developers, insurers. | Provincial Government, Technical Professionals, Manufacturers, Finance & Insurance/Business Services | 2025 | High | 9 | Reduction in redesign requests post-award Number of proposals with compliant stamped engineering | Provincial | Add requirement for stamped structural verification in all modular RFPs Provide bidders with local wind/snow/climate indices Require early coordination with Atlantic-licensed engineers
PM10 | Procurement Models and Contracts | Procurement Processes | Procurement is still oriented toward traditional construction, requiring significant effort to build acceptance for modular approaches. | Atlantic Region | Allow tenders to request modular alternatives so bidders can propose a modular option alongside traditional construction. | Provincial Procurement Divisions Provincial Housing Agencies Municipal Procurement Offices | Modular manufacturers, contractors, designers, cost consultants, municipal and provincial evaluators. | Provincial Government, Manufacturers, Municipal Government, Developers & General Contractors | 2026 | High | 8 | Number of tenders allowing modular alternatives Number of modular alternative submissions | Regional | Add optional modular submission line to tender documents Provide evaluators guidance on comparing modular vs traditional approaches
PM11 | Procurement Models and Contracts | Procurement Processes | Lack of value-based procurement approaches. | Atlantic Region | Add value-based evaluation factors such as schedule reliability, factory quality assurance, reduced site disruption, and repeatable design efficiency into modular-suitable tenders. | Provincial Procurement Divisions Provincial Housing Agencies Municipal Procurement Offices | Evaluators, modular manufacturers, contractors, architects, engineers, cost consultants. | Provincial Government, Manufacturers, Developers & General Contractors | 2026 | Medium | 9 | % of tenders with value-based scoring Increase in modular bids that reach evaluation stage Reduction in disqualification of modular proposals due to cost-only scoring | Regional | Identify value-based criteria relevant to modular (schedule, QA, site disruption) Update tender evaluation templates Train procurement staff on new evaluation weighting
PM12 | Procurement Models and Contracts | Procurement Processes | New modular entrants are not used to RFP processes. | NB | Provide bidders with a simple pre-submission checklist (what documents, drawings, certifications, and insurance are required) so new modular entrants understand what an RFP needs and can submit complete proposals. | NB Housing | Modular manufacturers (especially small/new ones), general contractors, procurement evaluators. | Manufacturers, Developers & General Contractors, Provincial Government | 2025 | High | 7 | Reduction in incomplete modular submissions Increase in number of modular bidders Fewer administrative RFIs | Provincial | Identify common missing/incorrect items in past submissions
PM13 | Procurement Models and Contracts | Procurement Processes | Lack of site access or information for bidders to accurately estimate on-site works. | NB | Develop an Modular Cost Libraries that provides standardized cost ranges and inputs for modular projects across the region (e.g., module $/sqft bands, transport and crane costs, installation costs, contingencies, island delivery uplifts, and seasonal adjustments). | Provincial Departments of Finance | Modular manufacturers, developers / builders, quantity surveyors, housing agencies (NB Housing, NSPHA, PEIHC, NLHC), lenders | Manufacturers, Developers & General Contractors, Provincial Government | 2026 -2028 | Medium | 8 | Number of manufacturers using the directory Reduction in estimate variability between suppliers Fewer lender RFIs about project costing | Regional | Collect baseline cost data from Atlantic manufacturers (module production, transport, installation). Create standardized cost bands (Low/Medium/High) for modules, logistics, and site work.
PM14 | Procurement Models and Contracts | Procurement Processes | Lack of schedule regulations and enforcements. | NB, PEI | Include specific schedule requirements in modular contracts such as site readiness dates, delivery windows, and installation milestones and link payments or holdbacks to meeting these dates. | NB Strategic Procurement PEI Procurement Provincial Housing Agencies Municipal Project Managers | Modular manufacturers, site contractors, crane companies, tansport companies, developers, project managers. | Provincial Government, Manufacturers, Transportation & Logistics Providers, Developers & General Contractors, Municipal Government | 2025 | High | 9 | Number of tenders including schedule enforcement Reduction in installation or delivery delays | Provincial, regional | Identify modular-specific scheduling needs Update contract templates to include enforceable schedule milestones
PM15 | Procurement Models and Contracts | Procurement Processes | Lack of flexible RFP formats - they are too structured and project specific. | NB | Use more flexible RFPs that define performance requirements rather than rigid, prescriptive drawings. | NB Strategic Procurement NB Housing | Modular manufacturers, architects, engineers, general contractors, developers. | Provincial Government, Manufacturers, Technical Professionals, Developers & General Contractors | 2026 | High | 8 | Number of RFPs using performance-based requirements Increase in modular submissions Reduction in redesign/change-order costs | Provincial | Identify which requirements can be performance-based instead of prescriptive Train evaluators on comparing modular proposals Update RFP templates to include flexible requirements
PM16 | Procurement Models and Contracts | Procurement Processes | Pre-fab work is often missing from trade agreements and scopes, making coordination harder. | Atlantic Region | Add modular-specific responsibilities (factory scope, interface points, connections, inspections, installation tasks) into trade scopes so site trades and manufacturers understand exactly what each party must deliver, preventing gaps and coordination issues. Standardized foundation/site-readiness checklist to reduce disputes and delays. | Provincial Procurement Divisions Provincial Housing Agencies | Modular manufacturers, subtrades (electrical, plumbing, HVAC, finishes), general contractors, inspectors, engineers, quantity surveyors. | Provincial Government, Manufacturers, Developers & General Contractors, Technical Professionals | 2026 | Medium | 8 | Fewer installation delays due to unclear responsibilities | Regional | Review typical modular scope boundaries (factory vs. on-site) Identify common interface failures on past projects Update procurement templates with modular-specific scope language
PM17 | Procurement Models and Contracts | Manufacturing and Supply Chain | Limited modular manufacturing capacity and an under-developed supply chain create dependency on imports, transport bottlenecks, and long lead times. | Atlantic Region | Issue bundled modular procurements (2–5 sites at once)so manufacturers can plan production months ahead, allocate factory slots to Atlantic orders, and stabilize transport and installation scheduling. Add regional laydown yards, harmonized escort-permit rules, and logistics training programs to reduce transport and installation bottlenecks. | Provincial Housing Agencies (NSPHA, NB Housing, PEIHC, NLHC) Provincial Procurement Divisions | Modular manufacturers, transport companies, crane operators, site contractors, developers, lenders, municipal partners. | Manufacturers, Provincial Government, Transportation & Logistics Providers, Developers & General Contractors, Finance & Insurance/Business Services, Municipal Government | 2026 | Medium | 9 | Number of sites included in bundled procurements Factory production allocated to Atlantic projects Reduction in transport delays | Regional
PM18 | Procurement Models and Contracts | Manufacturing and Supply Chain | The timing for servicing and installing utilities like power and gas is uncertain. | NB | Set confirmed utility servicing dates (power, water, sewer, gas) before tender award and require utility providers to meet these dates so modular installation isn’t delayed by late servicing. | NB Housing NB Power Utility Providers (gas, water) | Modular manufacturers, site contractors, utility companies, crane/transport teams, developers, municipal inspectors. | Manufacturers, Developers & General Contractors, Provincial Government, Municipal Government, Transportation & Logistics Providers | 2026 | Medium | 8 | Number of tenders with confirmed servicing dates Reduction in installation delays caused by utilities | Provincial | Early coordination meeting with utility providers Confirm servicing capacity and timelines
WD1 | Skilled Workforce and Development | Training & Skills Development | Lack of modular-specific training and education programs across colleges and trade schools. | Atlantic Region | Create a standardized modular construction curricula for trades schools (design, manufacturing, installation, logistics) | Provincial departments of advanced education Trade schools/colleges (NSCC, NBCC, Holland College, CNA) | Industry groups, trades schools/colleges, provincial government | Provincial Government, Industry Associations, Academic/Training Institutions, | 2027 | High | 8 | Number of participants completing mini-courses Number of certificates issued Employer satisfaction with trained workforce | Regional | Secure industry/trade school partnerships Develop modular course content and materials
WD2 | Skilled Workforce and Development | Training & Skills Development | Significant retraining is required to shift workers from traditional construction to modular. | Atlantic Region | Host modular construction mini-courses or workshops series for modular construction certificates. | Provincial departments of advanced education Trade schools/colleges (NSCC, NBCC, Holland College, CNA) Industry associations | Industry groups, trades schools/colleges, provincial government | Provincial Government, Academic/Training Institutions, Industry Associations | 2026-2027 | High | 7 | Number of participants completing mini-courses Number of certificates issued Employer satisfaction with trained workforce | Regional
WD3 | Skilled Workforce and Development | Training & Skills Development | Lack of clear, unified training pathways or standards for modular construction across Canada. | Atlantic Region | Develop a national standardized curriculum for OSC which aligns with national bodies such as CHBA. Align provincial apprenticeship bodies to recognize modular-specific credentials. | Canadian Home Builders’ Association (CHBA National) Provincial Apprenticeship Authorities (NS Apprenticeship, NB Apprenticeship, etc.) | Industry groups, trades schools/colleges | Industry Associations, Academic/Training Institutions | 2027 | Medium | 8 | Adoption rate of national curriculum by provinces Number of institutions offering courses Enrollment numbers | National, provincial | Align provincial apprenticeship bodies to recognize modular-specific credentials Establish CHBA alignment Approval by national training authorities Funding for curriculum development
WD4 | Skilled Workforce and Development | Training & Skills Development | NSCC programs closing due to low enrollment. | NS | Run targeted marketing campaigns highlighting the acclerating demand for workers in OSC | NSCC, Nova Scotia Department of Advanced Education Provincial marketing/communications offices | Trades schools/colleges | Academic/Training Institutions, Provincial Government | 2026 | Medium | 9 | Enrollment numbers in NSCC modular courses Campaign reach (social media, schools) Number of applications received | Local. provincial | Marketing campaign materials Coordination with NSCC and provincial education authorities
WD5 | Skilled Workforce and Development | Training & Skills Development | Barriers for foreign-trained workers to gain equivalency; limited culturally appropriate programs for Indigenous communities. | NS | Create streamlined credential-recognition pathways. Partner with Indigenous organizations to develop culturally appropriate OSC training programs within local communities. | Provincial Apprenticeship Authorities Indigenous organizations | Industry groups, trades schools/colleges, Indigenous organizations | Industry Associations, Indigenous & Community Organizations, Provincial Government, Academic/Training Institutions | 2026 | Medium | 8 | Number of foreign-trained workers completing recognition process Number of culturally appropriate programs delivered Participation by Indigenous students | Provincial, regional | Agreements with credentialing bodies Partnerships with Indigenous organizations Development of training content
WD6 | Skilled Workforce and Development | Skilled Trades & Labour Availability | Shortage of skilled trades needed for modular construction (design, assembly, mass timber, mechanical/electrical, etc.). | NB | Expand modular-focused trade training in colleges and unions, offer fast-track upskilling programs, and create industry-funded apprenticeships specific to modular roles. | New Brunswick Community College (NBCC) NB Department of Post-Secondary Education, Training, and Labour (PETL) Industry associations | Trades schools/colleges, industry groups | Provincial Government, Academic/Training Institutions, Industry Associations | 2027 | High | 8 | Number of apprenticeships created Program enrollment Industry placement rates | Regional | College/unions agreement Curriculum development Employer sponsorship secured
WD7 | Skilled Workforce and Development | Skilled Trades & Labour Availability | Low overall workforce availability limits the ability to scale modular construction. | Atlantic Region | Invest in automation within manufacutring facilites. Focus on OSC recruitment through public marketing campains and outreach within the construction industry. | Provincial Economic Development Departments Innovation, Science & Economic Development Canada Modular manufacturers Build Canada Homes | Provincial government, federal government, industry groups, Manufacturers | Provincial Government, Industry Associations, Manufacturers, Federal Government | 2026-2027 | Medium | 9 | Efficiency KPIs folllowing implementation of automation Output per worker Reduced labour bottlenecks | Local, regional | Investment in automation equipment Worker training on new technology
WD8 | Skilled Workforce and Development | Skilled Trades & Labour Availability | Rural factory locations limit labour access and reduce available workforce pools. | Atlantic Region | Offer financial incentives for relocation or financial support for housing (subsidies, etc) for facilities in rural areas. | Provincial Departments of Economic Development & Labour Employment and Social Development Canada (ESDC) Modular manufacturers | Provincial government, federal government, manufacturers | Provincial Government, Manufacturers, Federal Government | 2027 | Low | 7 | Number of relocation/housing subsidies granted Change in labour availability at rural facilities | Regional, local | Provincial/federal funding approval Policy design for incentives
WD9 | Skilled Workforce and Development | Skilled Trades & Labour Availability | Limited access to specialized equipment operators (e.g., cranes, certified operators). | Atlantic Region | Encourage regional collaboration across Atlantic provinces to share manufacturing capacity, transportation fleets, and material resources. | Provincial Departments of Transportation & Infrastructure Large transportation/logistics companies | Industry groups, transportation and logistics providers | Industry Associations, Transportation & Logistics Providers, Provincial Government | 2026 | Low | 8 | Counts of shared resources Project delays due to lack of resources | Regional | Coordination agreements between provinces Identification of regional capacity gaps
WD10 | Skilled Workforce and Development | Skilled Trades & Labour Availability | Few contractors have modular experience, limiting participation in projects. | NS | Facilitate knowlege sharing through conferences and forums. Create training modules for contractors through industry associations. | Provincial Construction Associations Modular manufacturers | Indusry groups, general contractors | Industry Associations, Manufacturers, Developers & General Contractors | 2026 | High | 8 | Attendance at forums Number of contractors completing training modules Feedback surveys | Regional | Development of training modules Industry association support
WD11 | Skilled Workforce and Development | Skilled Trades & Labour Availability | Staff shortages in public offices (planning, permitting, fire inspection) delay projects. | NB | Provide funding for additional municipal staffing, digitize permitting processes, and adopt pre-approved modular design |  | Municipal government, provincial government, federal government | Municipal Government, Provincial Government, Federal Government | 2027 | Medium | 9 | Number of municipal staff hired Permitting turnaround times Number of pre-approved designs adopted | Local, provincial | Budget approval Digital permitting system development Modular design approval templates
WD12 | Skilled Workforce and Development | Skilled Trades & Labour Availability | New building inspectors are inexperienced. | NL | Develop OSC-specific inspector training modules through collaboration with industry associations and experienced inspectors. | NL government: Department of Municipal and Community Affairs College of the North Atlantic | Trades schools/colleges, industry groups | Academic/Training Institutions, Provincial Government, Industry Associations | 2027 | Medium | 9 | Number of inspectors trained Inspector certification rates Reduced inspection delays | Provincial, regional | Collaboration with industry associations Curriculum development for inspector training
WD13 | Skilled Workforce and Development | Skilled Trades & Labour Availability | Noise restrictions and working-hour constraints affect labour availability. | NS | Optimize scheduling effiency such that quieter tasks take place in time when noise restrictions are in place. | Municipal governments Manufacturers | Manufacturers | Manufacturers, Municipal Government | 2026 | High | 6 | Compliance with noise scheduling Reduced labour downtime | Local | Development of optimized scheduling guidelines Coordination with local municipalities
WD14 | Skilled Workforce and Development | Skilled Trades & Labour Availability | Lack of on-island modular experts and off-site methods. | PEI | Host experts for training sessions to spread knowlege throughout the industry. Encourage collaboration across the Atlanic or maritime provinces. | Construction Association of PEI PEI Ministry of Housing, Land and Communities | Industry groups | Provincial Government, Industry Associations | 2026 | High | 8 | Number of training sessions hosted Number of attendees trained | Provincial | Workshop scheduling and content planning
WD15 | Skilled Workforce and Development | Awareness, Culture & Mindset | Workforce resistance to modular due to lack of familiarity, fear of job loss, or cultural hesitation toward new methods. | Atlantic Region | Host events promting OSC within the construction industry, hosted by respected industry professionals. Highlight how OSC allows for safer work environments, yearround manufacturing, and more stable working conditions | Provincial construction associations CHBA Atlantic Provincial Departments of Labour (for outreach funding) | Industry groups | Provincial Government, Industry Associations | 2026 | High | 8 | Attendance at OSC events Surveys on workforce perception of OSC Increased modular adoption | Regional, provincial | Identification of industry professionals to host events Event planning
WD16 | Skilled Workforce and Development | Awareness, Culture & Mindset | Low awareness and misconceptions about OSC quality, aesthetics, and durability. | Atlantic Region | Launch an awareness campain focused on educating the public on OSC (including open houses at manufacturing facilities) Develop an industry-wide marketing strategy with local case studies as examples. Require companies recieving public funding to contribute to educational outreach. | Provincial Departments of Housing & Communications CHBA Atlantic / CMHC / Build Canada Homes Manufacturers | Industry groups, provincial government, federal governement, manufacturers | Provincial Government, Industry Associations, Manufacturers, Federal Government | 2026-2027 | High | 9 | Public awareness metrics (survey data) Number of facility open houses Participation in outreach | National, regional, provincial | Marketing strategy developed Local case studies collected Cooperation from manufacturers
WD17 | Skilled Workforce and Development | Awareness, Culture & Mindset | Limited promotion of modular construction within the industry and workforce. | Atlantic Region | Host events promting OSC within the construction industry Provide sponsorships for tradespeople to attend events educating on OSC. Integrate OSC curriculum into existing training programs. | Provincial Construction Associations Trade schools/colleges Modular manufacturers Provincial Departments of Labour | Industry groups, trades schools/colleges, manufacturers | Industry Associations, Industry Associations, Manufacturers, Academic/Training Institutions | 2026-2027 | High | 8 | Number of OSC events held Number of sponsorships awarded and recipient career paths Training integration into programs | Regional, provincial, maybe national | Event planning and secured funding for sponsorships
WD18 | Skilled Workforce and Development | Workforce Retention & Recruitment | Workforce retention challenges linked to high living costs, housing affordability, and job security concerns in the modular sector. | Atlantic Region | Provide subsidized housing , establish multi-year government purchasing agreements to stabilize factory work and job security, offer raises or bonuses tied to experience and time at a company. | Provincial Housing Departments Employment and Social Development Canada (ESDC) Modular manufacturers | Provincial government, federal government, industry groups, Manufacturers | Provincial Government, Manufacturers, Federal Government, Industry Associations | 2027 | Low | 9 | Worker retention rates Housing uptake Employment stability metrics | Local, regional | Policy approval for housing subsidies Government purchasing agreements finalized
WD19 | Skilled Workforce and Development | Workforce Retention & Recruitment | Difficulty attracting youth, women, diverse groups, and newcomers to modular construction trades. | Atlantic Region | Support targeted scholarships or application waivers for underrepresented groups. Provide mentorship programs for underrepresented groups. Require DEI and anti-racism training for companies to recieve funding. Include DEI training in trades programs | Provincial Departments of Labour & Advanced Education Federal Women and Gender Equality Canada (WAGE) Trade schools/colleges Modular manufacturers | Municipal, provincial, federal governments, manufacturers, trades schools/colleges | Municipal Government, Provincial Government, Academic/Training Institutions, Manufacturers, Federal Government, Indigenous & Community Organizations | 2026-2027 | Medium | 9 | Scholarship uptake Mentorship participation Diversity metrics in workforce | Provincial, regional | Funding approval for scholarships Mentorship program structure
WD20 | Skilled Workforce and Development | Workforce Retention & Recruitment | Culturally inappropriate or unwelcoming workplaces limit participation from First Nations and underrepresented groups. | NB | Support Indigenous-owned business development Require DEI and anti-racism training for companies to recieve funding. Include DEI training in trades programs | NB Department of Post-Secondary Education, Training, and Labour (PETL) Wolastoqey and Mi'kmaq business organizations NBCC and training institutions Industry associations | Municipal, provincial, federal governments, manufacturers, trades schools/colleges | Provincial Government, Federal Government, Academic/Training Institutions, Indigenous & Community Organizations | 2026-2027 | High | 8 | Number of Indigenous-owned businesses supported DEI training completion Workforce participation rates | Provincial, regional | Funding and program approval DEI curriculum developed
TL1 | Transportation and Logistics | Module size and road restrictions | Escort and permit rules for oversized modules (often >12 ft wide) differ between jurisdictions. | Atlantic Region | Create provincial or regional modular housing transport agreements to harmonize escort/permit requirements across municipalities. | Provincial Departments of Transportation Municipal transportation departments | Provincial government, municipal governments, transportation and logistics providers, general contractors | Provincial Government, Municipal Government, Transportation & Logistics Providers, Developers & General Contractors, Municipal Government | 2026 | Medium | 9 | Number of agreements signed Reduced delays due to permit harmonization Number of municipalities participating | Local, provincial, regional | Regulatory coordination between provinces Legal framework for transport agreements
TL2 | Transportation and Logistics | Module size and road restrictions | Module width/height is constrained by bridge clearances, turning radii, and road widths | Atlantic Region | Maintain a database of known infrastrucutre conflict points for ease of planning transportation. Opt for panelized construction or methods other than volumetric modular when conditions are not condisive to transporting modules. | Provincial Departments of Transportation & Infrastructure Municipal public works departments Utility companies Transportation/logistics providers | Utility companies (power, telecommunications, etc), provincial governments, municipal governments, transportation and logisitics providers, general contractors, owners | Transportation & Logistics Providers, Developers & General Contractors, Provincial Government, Municipal Government | 2026-2027 | Medium | 7 | Database completeness Reduced transport delays | Provincial, local | Data collection on bridges, roads, turning radii Mapping infrastructure conflicts
TL3 | Transportation and Logistics | Module size and road restrictions | Seasonal weight restrictions | Atlantic Region | Plan deliveries around seasonal weight restriction periods. Coordinate with local authorities for possible temporary exemptions or permits during seasonal weight restrictions. | Provincial Departments of Transportation Municipal permitting offices General contractors | General contractor, provincial governments | Provincial Government, Developers & General Contractors | 2026-2027 | Low | 8 | Number of deliveries adjusted around restrictions Reduced seasonal delays | Provincial | Schedule coordination with authorities Awareness of seasonal restriction periods
TL4 | Transportation and Logistics | Module size and road restrictions | Modules must be designed to match available island transport equipment. | NL | Develop a pre-approved design catalogue that establishes standard modular dimensions aligned with local transportation regulations and local equipment availability. Establish early coordination between designers, manufacturers, and transport providers to ensure compatibility. | NL Department of Transportation amd Infrastructure NL Housing Corporation Industry associations Build Canada Homes | Industry associations, provincial government, municipal governments, federal government | Provincial Government, Industry Associations, Municipal Government, Federal Government | 2027 | Medium | 9 | Adoption of pre-approved designs Reduced transport delays | Local, regional, national | Design catalogue development Coordination between designers, manufacturers, transport providers
TL5 | Transportation and Logistics | Module size and road restrictions | Ferry costs add major expense for panelized construction. | NL | Provide discounted or off-peak ferry rates for approved OSC housing component transportation | NL Department of Transportation & Infrastructure Marine Atlantic | Provincial government, transportation and logistics providers | Provincial Government, Transportation & Logistics Providers | 2027 | High | 8 | Number of ferry trips using discounted/off-peak rates Cost savings On-time deliveries | Provincial | Agreements with ferry operators Approval of subsidy program
TL6 | Transportation and Logistics | Module size and road restrictions | Poor detour roads increase delivery risk. | NB | Invest in maintinaing a modular delivery specifc routes to a high quality. Maintain a database of known infrastrucutre conflict points for ease of planning transportation. | New Brunswick Department of Transportation and Infrastructure (DTI) Logistics providers | Provincial government, transportation and logistics providers | Provincial Government, Transportation & Logistics Providers | 2027 | Low | 8 | Condition of delivery routes Reduced transport incidents Maintenance logs | Provincial | Identification of modular delivery routes Allocation of maintenance funding
TL7 | Transportation and Logistics | Module size and road restrictions | No standardized dimensions for local modular practice. | NS | Develop a pre-approved design catalogue that establishes standard modular dimensions aligned with local transportation regulations. | Nova Scotia Department of Public Works | Industry associations, provincial government, municipal governments, federal government | Industry Associations, Provincial Government, Municipal Government, Municipal Government | 2027 | Medium | 9 | Pre-approved design adoption Reduced transport-related issues | Local, regional, national | Development of standard modular dimensions Coordination with local authorities
TL8 | Transportation and Logistics | Module size and road restrictions | HRM has distinct escort/permit timing from rural NS. | NS | Create provincial or regional modular housing transport agreements to harmonize escort/permit requirements across municipalities. | Nova Scotia Department of Public Works | Provincial government, municipal governments, transportation and logistics providers, general contractors | Provincial Government, Municipal Government, Transportation & Logistics Providers, Developers & General Contractors | 2026 | Medium | 8 | Number of transport agreements signed Reduced permit delays | Local, provincial, regional | Provincial/regional coordination Legal framework established
TL9 | Transportation and Logistics | Module size and road restrictions | Larger modules require police escorts; delays occur when escorts leave | NS | Develop a pre-approved route registry for modular loads with standard permitting and reduced police escort requirements. | Nova Scotia Department of Public Works HRM Transportation and Public Workds Municipalities | Provincial government, municipal governments, transportation and logistics providers, general contractors | Provincial Government, Transportation & Logistics Providers, Developers & General Contractors, Municipal Government | 2026-2027 | Medium | 9 | Number of pre-approved routes Reduced police escort requirements Transport time savings | Local, provincial | Mapping of routes Coordination with police and municipal authorities
TL10 | Transportation and Logistics | Damage and Protection | Inconsistent moisture barriers and wrapping practices. | Atlantic Region | Establish best practices for transporting modules or other OSC products. Offer training/certification for factory staff and transportation providers on best-practice transportation protection. | Academic and training institutions CHBA | Manufacturers, transportation and logistics providers, general contractors, CHBA or construction associations(?), trades schools/colleges, academic institutions | Manufacturers, Transportation & Logistics Providers, Academic/Training Institutions, Industry Associations | 2027 | Medium | 8 | Number of staff trained Reports of damage to modules during transportation Compliance with best practices | National | Development of transport best-practice guide Training program preparation
TL11 | Transportation and Logistics | Damage and Protection | Responsibility/liability for damage is unclear between manufacturer, hauler, GC. | Atlantic Region | Establish the roles and responsbilities (including liability) through a formal agreement and proper insurance coverage for all parties | Industry associations Insurance companies | General contractors, manufacturers, owners, transportation and logistics providers | Industry Associations, Developers & General Contractors, Transportation & Logistics Providers, Manufacturers, Finance & Insurance/Business Services | 2026 | High | 7 | Reduction in disputes | Local | Development of formal insurance and liability agreements Stakeholder alignment
TL12 | Transportation and Logistics | Damage and Protection | Denting, corner damage, and structural movement during loading/unloading. | Atlantic Region | Establish best practices for transporting modules or other OSC products. Offer training/certification for factory staff and transportation providers on best-practice transportation protection. | Manufacturers Transportation/logistics providers CHBA National (framework for best practices) Trade schools/colleges (training) | Manufacturers, transportation and logistics providers, general contractors, CHBA or construction associations(?), trades schools/colleges, academic institutions | Manufacturers, Transportation & Logistics Providers, Developers & General Contractors, Academic/Training Institutions, Industry Associations | 2027 | High | 8 | Number of training sessions delivered Reports of damage to modules during transportation | National | Transport best-practice guidelines finalized Training content developed
TL13 | Transportation and Logistics | Damage and Protection | Heavy machinery causes soil compaction and clearing. | NS | Establish clear best practice guidelines for low-impact staging areas and post-installation soil remediation. Subsidize investments in equipment (e.g. mats) to reduce soil compaction | Nova Scotia Department of Environment & Climate Change Natural Resources Canada (funding for low-impact equipment) | Provincial and federal governments, research institutions, industry groups | Provincial Government, Federal Government, Academic/Training Institutions, Industry Associations | 2027 | Medium | 8 | Reduction in soil compaction incidents Number of subsidized equipment purchases | National, regional | Development of low-impact staging guidelines Funding approval for equipment subsidies
TL14 | Transportation and Logistics | Site access and Storage constraints | Limited staging and storage space near construction sites. | Atlantic Region | Establish designated temporary staging yards. Improve scheduling efficiency for closer timeline between manufacturing completion and site delivery; use digital tools to optimize logistics planning, routing, scheduling, and load coordination. Coordinate with municipalities to designate small-scale staging areas for short periods of time. | Municipal governments (zoning, temporary yard designation) Provincial Departments of Transportation (coordination) GC/transportation providers | General contractor, transportation/logistics provider, municipal governments, provincial governments, manufacturers, property owners | Municipal Government, Developers & General Contractors, Manufacturers, Transportation & Logistics Providers | 2026 | Low | 8 | Number of staging yards designated Reduction in delivery delays Improvement in on-time module deliveries | Local, provincial | Database of land potentiall available for staging near sites
TL15 | Transportation and Logistics | Site access and Storage constraints | Conflicts with power lines, telecommunications, and fire marshal requirements. | NB | Maintain a database of known infrastrucutre conflict points for ease of planning transportation. Opt for panelized construction or methods other than volumetric modular when conditions are not condisive to transporting modules. | New Brunswick Office of the Fire Marshal NB Department of Transportation & Infrastructure | Utility companies (power, telecommunications, etc), provincial governments, municipal governments, transportation and logisitics providers, general contractors, owners | Provincial Government, Transportation & Logistics Providers, Developers & General Contractors, Municipal Government | 2026-2027 | Medium | 7 | Number of conflicts identified in database Reduction in transport delays due to conflicts | Local, provincial | Database of infrastructure conflict points developed
TL16 | Transportation and Logistics | Site access and Storage constraints | Difficult access in dense urban areas (tight roads, overhead utilities). | NS | Opt for panelized construction or methods other than volumetric modular when conditions are not condisive to transporting modules. Consider temporary road closure or nighttime deliveries if necessary | Halifax Regional Municipality (HRM) | General contractor, transportation/logistics provider, municipal government, manufacturer | Municipal Government, Developers & General Contractors, Manufacturers | 2026 | High | 8 | Number of temporary road closures approved Number of nighttime deliveries completed safely | Local | Owners, GCs, and manufacturers must be adaptable to the methods of construction most suitable for specific cases
Note on F5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Similar guidance tools exist in BC modular building permitting guide for MMC approvals.
Note on F8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Similar navigator-style roles exist in BC, Ontario, Nova Scotia and CMHC to help resolve outdated processes and guide complex housing approvals.
Note on F17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: In UK Atelier has lending guides for MMC projects https://webcdn.atelierfinance.co.uk/media/ujefkjkq/offsite-and-modular-construction-lending-guide.pdf

## Opportunities from Workshops
ID | Category | Opportunities/ Initiative from workshops
PR1 | Policy and Regulatory | • Reduce red tape to speed up processes • Ensure governments own policies do not run counter to increasing supply (e.g. interest rates, taxation, codes and standards) • Invest in R&D for lower or cost neutral solutions to be pursued before regulation that increases cost. • Avoid adding costs through code changes • Increase communication between departments on changes and proposals • Increase access to public lands for affordable housing • Increase consultation with non-profits on community needs (“nothing about us without us”) • Promote ADUs in certain zoning areas • Increase consumer awareness of OSC product types • Consider promoting multi-generational housing when appropriate • Adapt use of existing buildings • Increase private-public partnerships and government incentives for housing • Create example codes/by-laws for municipalities to adapt, improve cross- jurisdictions regulations. • Ensuring uniformity and compliance in regulations across all municipalities. • Create CSA certification rebate programs to increase of certified pants • NS - Leverage Preferred builder program for accelerated permitting process which benefits builders at scale/repetition like OSC. • NS - Leverage testing result requirements to occupancy to unburden initial permitting and hold construction to account, thereby unburdening building inspectors that may not be familiar with OSC.
PR2 | Policy and Regulatory
PR3 | Policy and Regulatory
PR4 | Policy and Regulatory
PR5 | Policy and Regulatory
PR6 | Policy and Regulatory
PR7 | Policy and Regulatory
PR8 | Policy and Regulatory
PR9 | Policy and Regulatory
PR10 | Policy and Regulatory
PR11 | Policy and Regulatory
PR12 | Policy and Regulatory
PR13 | Policy and Regulatory
PR14 | Policy and Regulatory
PR15 | Policy and Regulatory
FI1 | Financing and Insurance | • Funding for developers from Accelerator Fund • Bridge financing from CMHC • Ensure proper planning of OSC projects to reduce costs • Utilize funding programs through Build Canada Homes • Use standardization to lower risks for insurers (lower rates) • NL - Updating in financial institutions to support modular/OSC • NB - Opportunity for municipal grants to offset costs • PEI - Remove development costs for supportive housing • NS - Relaxing requirements necessary to recognize modular homes as permanent homes
FI3 | Financing and Insurance
FI4 | Financing and Insurance
FI6 | Financing and Insurance
FI7 | Financing and Insurance
FI9 | Financing and Insurance
FI10 | Financing and Insurance
FI11 | Financing and Insurance
FI12 | Financing and Insurance
FI13 | Financing and Insurance
FI14 | Financing and Insurance
FI15 | Financing and Insurance
FI16 | Financing and Insurance
FI17 | Financing and Insurance
FI18 | Financing and Insurance
FI19 | Financing and Insurance
FI20 | Financing and Insurance
FI21 | Financing and Insurance
FI22 | Financing and Insurance
FI23 | Financing and Insurance
PM1 | Procurement Models and Contracts | • Develop clear, standardized procurement frameworks and contract templates tailored to modular and off-site construction. • Shift toward value-based selection methods that evaluate project performance and long-term outcomes instead of lowest bid. • Adopt flexible procurement approaches such as design-build, progressive design-build, and integrated project delivery (IPD) to support modular delivery. • Strengthen collaboration and risk-sharing between manufacturers, contractors, and clients within contracts. • Improve awareness and technical understanding of modular procurement among government agencies and municipalities. • Publish provincial or regional procurement best-practice guides focused on off-site construction. • Align procurement scheduling and production planning to minimize delays and cost overruns. • Coordinate regionally to share qualified modular suppliers and bidder lists. • Integrate modular procurement language and expertise into public-sector contracting frameworks. • NS: Apply lessons from shipbuilding and large industries to improve modular contracting. • NS: Pilot fixed-rate procurement cycles to give suppliers predictable pricing windows. • PEI: Adapt procurement models to accommodate PEI’s limited manufacturing capacity and smaller market size, ensuring processes remain flexible and scalable. • PEI: Remove restrictive tendering rules or specification requirements that unintentionally exclude modular manufacturers from bidding. • NB: Create simplified procurement pathways specifically designed to support not-for-profit and community developers that lack capacity to navigate complex RFP structures.
PM2 | Procurement Models and Contracts
PM3 | Procurement Models and Contracts
PM4 | Procurement Models and Contracts
PM5 | Procurement Models and Contracts
PM6 | Procurement Models and Contracts
PM7 | Procurement Models and Contracts
PM8 | Procurement Models and Contracts
PM9 | Procurement Models and Contracts
PM10 | Procurement Models and Contracts
PM11 | Procurement Models and Contracts
PM12 | Procurement Models and Contracts
PM13 | Procurement Models and Contracts
PM14 | Procurement Models and Contracts
PM15 | Procurement Models and Contracts
PM16 | Procurement Models and Contracts
PM17 | Procurement Models and Contracts
PM18 | Procurement Models and Contracts
WD1 | Skilled Workforce and Development | • Expand modular and off-site construction training in trade schools, colleges, and universities. • Introduce targeted up-skilling, micro-credentials, and apprenticeships for modular manufacturing and installation. • Strengthen collaboration among government, educational institutions, and industry to develop modular-specific training pathways. • Increase public and professional awareness of modular construction through education and outreach. • Address skilled labour shortages through cross-trade, multi-disciplinary training. • Support inclusive, diverse, and gender-equitable participation in construction trades and technical programs. • NS: Partner NSCC with modular manufacturers to create dedicated modular design and construction programs. • NS: Incentivize apprenticeships with wage subsidies and guaranteed placements aligned to modular delivery. • PEI: Apply a tiered upskilling model (inspired by BC) tailored to PEI’s smaller workforce scale. • NB: Engage First Nation youth through modular apprenticeships and inclusive workforce programs. • NL: Facilitate direct apprenticeships with modular manufacturers operating within or partnering with NL. • NL: Offer external exposure opportunities (e.g., UK modular programs, London Build) to bring innovation back to the province.
WD2 | Skilled Workforce and Development
WD3 | Skilled Workforce and Development
WD4 | Skilled Workforce and Development
WD5 | Skilled Workforce and Development
WD6 | Skilled Workforce and Development
WD7 | Skilled Workforce and Development
WD8 | Skilled Workforce and Development
WD9 | Skilled Workforce and Development
WD10 | Skilled Workforce and Development
WD11 | Skilled Workforce and Development
WD12 | Skilled Workforce and Development
WD13 | Skilled Workforce and Development
WD14 | Skilled Workforce and Development
WD15 | Skilled Workforce and Development
WD16 | Skilled Workforce and Development
WD17 | Skilled Workforce and Development
WD18 | Skilled Workforce and Development
WD19 | Skilled Workforce and Development
WD20 | Skilled Workforce and Development
WD21 | Skilled Workforce and Development
TL1 | Transportation and Logistics | • Increase modular manufacturing capacity to relieve factory bottlenecks and support consistent transport-ready output. • Improve productivity at the facility level to enable timely logistics, smoother dispatching, and faster delivery. • Encourage regional collaboration across Atlantic provinces to share manufacturing capacity, transportation fleets, and material resources. • Support local production of modular components (wall systems, insulation, structural panels) to reduce shipping costs and reliance on imported materials. • Promote “shell-only” modular delivery models to simplify transport and rely on local contractors for finishing, reducing transport complexity. • Use AI and digital tools to optimize logistics planning, routing, scheduling, and load coordination. • Showcase modular transport and installation methods through public expos, demonstrations, and education sessions to improve awareness. • NS: Cubit produces SIPs (Structural Insulated Panels) supplying most modular materials in-province. • NS: Pre-chased, pre-installed, pre-vapor-barriered wall panels reduce inspection and skill needs. • PEI: Hillsborough land assembly (50 acres shovel-ready for modular development). • PEI: Higher-end mini homes (16′ width) designed for single-truck delivery. • NB: Create provincial platforms such as NCCAs Expo to promote modular transport education and showcase local production.
TL2 | Transportation and Logistics
TL3 | Transportation and Logistics
TL4 | Transportation and Logistics
TL5 | Transportation and Logistics
TL6 | Transportation and Logistics
TL7 | Transportation and Logistics
TL8 | Transportation and Logistics
TL9 | Transportation and Logistics
TL10 | Transportation and Logistics
TL11 | Transportation and Logistics
TL12 | Transportation and Logistics
TL13 | Transportation and Logistics
TL14 | Transportation and Logistics
TL15 | Transportation and Logistics
TL16 | Transportation and Logistics

## Location
ATL
NB
NL
NS
PEI

## Scope of Implementation
local
provincial
regional
national